## FORM-FIT UP
[8 empty] | PROJECT REPORT NO. : |  |  |  | LL1-FIR-PP/FU-WEC-C-1000-4430
FIELD INSPECTION REPORT | [7 empty] | LL1-2Q24-558
INSPECTION ITEM : | [6 empty] | PROJECT : | Package D LLDPE
FIT UP REPORT | [6 empty] | JOB NO. : | F047
[7 empty] | PLANT : | Long Son Island, Vietnam
[7 empty] | REF NO. : | LL1-FIR-PP/FU-WEC-C-4000-4558
SIGNATURE
INSPECTION NOTICE NO. |  | : | LL1-2Q42-558 |  |  |  | SUBCONT. | CONTRACTOR |  | COMPANY
COMPANY 'S INSPECTOR |  | : |  |  |  |  | 2021-02-19 | 2021-02-19 |  | / /
CONTRACTOR 'S INSPECTOR |  | : | Đào Minh Duân
SUBCONTRACTOR |  | : | Lê Văn Sơn/Phạm Văn Sơn | [6 empty] | N/A
ITP NO. : 3.03.03
AREA : Pipe rack 4000
SUBCONTRACTOR : WE Construction |  |  | Date : | 2021-02-19 |  |  | R | *
No. | Iso. Dwg. No. | Sheet | Rev. | Joint No. | Size | Type | Spool No. | Shop/ Field | DB |  | Remark
1 | 4000-IA-93C19-01-1/2 | 1/2 | 1 | 001 | 2 | SOF | 4000-00031 | S | 2
2 | 4000-IA-93C19-01-1/2 | 1/2 | 1 | 002 | 3/4 | OL | 4000-00031 | S | 0.75
3 | 4000-IA-93C19-01-1/2 | 1/2 | 1 | 006 | 2 | SOF | 4000-00031 | S | 2
4 | 4000-IA-93C19-01-1/2 | 1/2 | 1 | 007 | 2 | SOF | 4000-00032 | S | 2
5 | 4000-IA-93C19-01-1/2 | 1/2 | 1 | 008 | 2 | SOF | 4000-00032 | S | 2
6 | 4000-LS-95D61-01-3/10 | 3/10 | 1 | 005 | 1/2 | OL | 4000-00661 | S | 0.5
7 | 4000-LS-95D61-01-3/10 | 3/10 | 1 | 006 | 1/2 | OL | 4000-00661 | S | 0.5
8 | 4000-LS-95D61-01-3/10 | 3/10 | 1 | 007 | 1/2 | OL | 4000-00661 | S | 0.5
9 | 4000-LS-95D61-01-3/10 | 3/10 | 1 | 008 | 1/2 | OL | 4000-00661 | S | 0.5
[8 empty] | Total DB |  | 10.75
|  | R | Accepted |  |  | £ | Rejected
STANDARD FORM NO. SF-430-01-G01 | [5 empty] | Rev. 1 Date 26 Dec 2019
SHOP
FIELD

## FIN
[8 empty] | FIELD INSPECTION NOTICE | [11 empty] | PROJECT NOTICE NO. :
LL1-2Q42-558
(COMPANY's Representative) | [13 empty] | PROJECT |  |  | : | Package D LLDPE
ATTN : | [13 empty] | JOB NO. |  |  | : | F047
| Nguyen Duc Thien Le Luong Bao Tung | [12 empty] | PLANT |  |  | : | Long Son Island, Vietnam
[14 empty] | REF No. |  |  | : | LL1-FIN-PP/FU-WEC-C-000-4558
[14 empty] | ISSUE DATE : |  |  |  | 2021-02-19
INSPECTION NOTIFICATION :
We would like to have your presence for inspection according to the following schedule.
| Inspection Grade : | [5 empty] | ( ) A : Require COMPANY's Witness | [8 empty] | ( ) B : Require CONTRACTOR's Witness
| Requirement witness of the concerned local authority (ies) | [14 empty] | ( ) Yes |  |  |  |  | ( x ) No
| Date : |  | 2021-02-19 | [5 empty] | Time : |  | 10h AM |  |  |  | Duration : |  | 4 Hours
| Work Area : |  |  |  | Package D Pipe Stocking Area | [8 empty] | Subcontractor Company : | [5 empty] | WE Construction
| Category : |  |  |  | ( ) | Civil | [5 empty] | ( ) | Steel Structure | [6 empty] | ( ) | Electrical
[5 empty] | ( ) | Building | [5 empty] | ( ) | Tank Erection | [6 empty] | ( ) | Instrument
[5 empty] | ( ) | HVAC | [5 empty] | ( ) | Equipment Installation | [6 empty] | ( ) | Painting
[5 empty] | ( ) | Fire Protection | [5 empty] | ( x ) | Piping | [6 empty] | ( ) | Insulation
( )
| ITP No. | [8 empty] | Commodity/Item No. | [5 empty] | Inspection Activities
|  |  |  | 3.03.03 | [6 empty] | Piping Work | [6 empty] | Fit-up Inspection
Area : Pipe Rack 4000
| LE VAN SON | [17 empty] | DAO MINH DUAN
| ( | [7 empty] | ) |  | ( |  |  |  |  | ) |  | ( |  |  |  | )
| Subcontractor | [9 empty] | Superintendent | [6 empty] | Field Quality Control
ACKNOWLEDGEMENT OF COMPANY
Kindly put in [ ] as [ X ] where applicable and return this sheet with information of your inspector,
and with your signature.
|  |  | [ ] |  | 1. | We will attend the above inspection.
|  |  | [ ] |  | 2. | We will waive the above inspection.
|  |  | [ ] |  | 3. | We will postpone the above inspection to
Date
COMPANY's Inspector Name
|  |  | 1 | [12 empty] | COMPANY 's Signature
|  |  | 2 | [12 empty] | Date :
FORM NO. | [7 empty] | F047-430-01-G03 |  |  |  |  | Rev. 1 |  |  | Date |  | 26 Dec 2019

## Cover
PETROCHEMICAL COMPLEX
IN SOUTH OF VIETNAM,
TỔ HỢP HÓA DẦU MIỀN NAM VIỆT NAM
Long Son Petrochemicals Co., Ltd | [6 empty] | [PACKAGE D]
| Contract No: …. | [5 empty] | INSPECTION RECORD SHEET |  |  | Page: |  | Project No: Package D LLDPE
| Hợp đồng số: LSP-CA-132 | [5 empty] | BIÊN BẢN NGHIỆM THU |  |  | Trang: |  | Dự án số: F047
1 of 1
Doc.No: |  |  |  | Rev. |  |  | Inspection Record No.: |  |  |  | Doc.No: |  |  |  |  | Rev.:
Tài liệu số: |  |  |  | Lần xuất bản: |  |  | Hồ sơ nghiệm thu số: |  |  |  | Tài liệu số: |  |  |  |  | Lần xuất bản:
2
LL1-2Q92-0060 |  |  |  |  | 1 | [5 empty] | LL1-2Q92-0060-G000 | [5 empty] | c
1: | Name of Inspection Item / Tên hạng mục được nghiệm thu: Fit-up inspection (3.03.03) / Nghiệm thu Fit-up (3.03.03)
2. Date of Inspection / Thời gian nghiệm thu: | [7 empty] | 3. Location of Inspection / Địa điểm nghiệm thu: LLDPE
| 2021-02-19 |  |  | / | 2021-02-19 |  |  |  | Plant – LSP Project - Package D/ Nhà máy LLDPE-Dự án
LSP-Gói D
No. STT |  | Inspection work Công việc nghiệm thu | [5 empty] | Inspection Report No. |  |  | Conclusion |  |  |  | Remark/ Ghi chú
Kết luận nghiệm thu
[8 empty] | BB nghiệm thu số: |  |  | (ACC/ACW/REJ)
1 |  |  | Fit-up inspection (3.03.03) |  |  |  |  | LL1-2Q24-558 |  |  | ACC |  |  |  | See attachment/
|  |  | Nghiệm thu Fit-up (3.03.03) | [11 empty] | Xem đính kèm
Note: ACC – Accepted. ACW – Accepted with Punch, work can be proceeded. REJ – Rejected.
ACC – Chấp thuận ACW – Chấp thuận có điều kiện, công việc vẫn được tiến hành REJ – Hủy bỏ
In case the inspection work(s) is/are accepted with comment (ACW), please write down the punches in detail and specify the grade of punch (A / B / C) / Trong trường hợp hạng mục được nghiệm thu có điều kiện (ACW), vui lòng nêu rõ các tồn đọng một cách chi tiết và ghi rõ loại tồn đọng (A / B / C).
Subcontractor’s | [5 empty] | The EPC Contractor/ Tổng thầu
Technician (or QC inspector) | [5 empty] | Contractor’s Technician (or QC inspector) | [6 empty] | Witness by Company
Cán bộ kỹ thuật | [7 empty] | Contractor’s Supervision/ |  |  |  |  | (if required) / Chứng kiến
hoặc kỹ sư chất lượng của | [5 empty] | Cán bộ kỹ thuật |  | Cán bộ giám sát của tổng thầu |  |  |  |  | của Chủ đầu tư (nếu có)
thầu phụ | [5 empty] | hoặc kỹ sư chất lượng của tổng thầu | [6 empty] | Referred to approved ITP
| Signature: | [5 empty] | Signature: |  | Signature: |  |  |  |  | Signature:
| Full name: Le Van Son | [5 empty] | Full name: Dao Minh Duan |  | Full name: …..................... |  |  |  |  | Full name: …................
Date: |  | 2021-02-19 |  |  |  | Date: | 2021-02-19 |  | Date: …......./…...…....../…… |  |  |  |  | Date: …......./…...…....../……
Subcontractor’s Name: WEC | [6 empty] | Contractor’s Name: TTCL |  | Contractor’s Name: TTCL |  |  |  |  | Company’s Name: LSP
Instruction: The inspection items specify in the table above shall be (i) same work category, (ii) Same inspection date, (iii) Same inspection location, and its inspection reports is a part of this inspection record
Formulas:
INSPECTION RECORD SHEET = [Inspection work Công việc nghiệm thu]